## >$200
Projects in Progress - over $200,000 | JCOS Approval Req'd Approved | Original Budget | Revised Project Budget | Actual Expenditures to Date | Forecast of Final Cost
University Student Housing | Yes 10/17/2000 | 21000000 | 21000000 | 20853689 | 21000000
Fund Number 70514,70608,70609
Status: Construction Punch List
Projected Completion Date: November 2005
Comment: Landscape Improvements in progress - 95%
Comment: Lightning Protection in progress - 95%
Meadow Brook Hall Repairs/Renovation Project | Yes 6/17/2005 | 7000000 | 7000000 | 1101834 | 7000000
Fund Number 70589
Status: Construction - 13%
Projected Completion Date: October 2006
Primary Electric Power | Yes 12/2001 | 4800000 | 4800000 | 4790055 | 4800000
Fund Number 70523, 70577, 70557, 70549, 70561, 70572
Status: To be closed in next 30 days
Projected Completion Date: October 2005
Comment: 4 revisions reducing allocation
Vandenberg Hall Dining Renovation | Yes 4/21/2005 | 1500000 | 1571000 | 1450338 | 1571000
Fund Number: 70612 | Revised and Approved 9/29/05
Status: Construction - 99% closing out punch list
Projected Completion Date: August 2005
Comment: $1.3M of funds from Food Vendor
Comment: $200,000 of funds from Department
Comment: $71,000 need for abatement issues add to project
South Foundation Hall Classroom Improvements | No | 481000 | 521000 | 311435 | 521000
Fund Number 70592
Status: Construction - 99% paper work needed to finish
Projected Completion Date: August 2005
Comment: Additional technology added
Golf Course Bridge Replacement | No | 20000 | 324000 | 290743 | 324000
Fund Number 70587
Status: To be closed in next 60 days
Project Completion Date: June, 2005
Comment: Increase occurred after eng'g completed
TOTAL PROJECTS IN PROGRESS |  | 34801000 | 35216000 | 28798094 | 35216000
Notes:
1. Revised Project Budget equals the Original Budget plus all approved changes to the budget.
2. Projects are added to the report when a funding source has been identified and a plant fund account authorized for the project.
3. The project status will be reported as "Completed" when the "actual expenditures to date" equals the "forecast", TMA work
order system ties to Banner, and no additional expenditures or work is anticipated on the project.
4. A project whose status has been reported as complete to the Board, will be removed from the report for the next Board meeting.

## >$50
Projects in Progress - over $50,000 | JCOS Approval Req'd Approved | Original Budget | Revised Project Budget | Actual Expenditures to Date | Forecast of Final Cost
P-41S Lot Re-paving | No | 198000 | 198000 | 127419.17 | 198000
Fund Number 70599
Status: To be closed in next 60 days
Project Completion Date: September, 2005
Upper Play Fields Improvement | No | 150000 | 199680 | 169055 | 199680
Fund Number 70581
Status: Construction 60% completed
Project Completion Date: October, 2005
Comments: Inadequate original estimate
Sidewalks Repairs | No | 60000 | 198000 | 189315 | 198000
Fund Number 70577
Status: To be closed in next 30 days
Project Completion Date: August, 2005
Comment: Paying final invoices
Fire Safety Doors | No | 73000 | 198000 | 139683 | 198000
Fund Number 70506
Status: To be closed in next 30 days
Project Completion Date: October, 2005
Comment: Waiting on ADA door closer installation
Hannah Hall Exterior Column Restoration | No | 150000 | 188000 | 11113 | 188000
Fund Number 70606
Status: Construction 30% completed
Project Completion Date: October, 2005
MBT/Golfview Paving Replacement | No | 182000 | 182000 | 0 | 182000
Fund Number 70616
Status: Out for bids
Project Completion Date: Novemeber 2005
Viron Additional ECM's | No | 110000 | 187040 | 181466 | 187040
Fund Number 70503
Status: 99% working on punch list
Project Completion Date: November 2005
NFH IT HVAC | No | 80000 | 186584 | 170686 | 186584
Fund Number 70588
Status: Construction - Punch List - 90%
Projected Completion Date: Septmeber, 2005
Comments: Waiting on punchlist items
ODH Roof Repair | No | 180000 | 180000 | 176235 | 176235
Fund Number 70572
Status: To be closed in next 30 days - letter sent
Project Completion Date: August 2005
Storm Water Study | No | 180000 | 180000 | 157861.68 | 180000
Fund Number: 70578
Status: Study being updated; ongoing permit-related activities
Project completion: March, 2006
Sunset Terrace Roof Replacement | No | 172000 | 172000 | 7413 | 172000
Fund Number: 70610
Status: Construction 99% working on punch list
Project Completion Date: September 2005
Comments: Insurance claim is being worked on
Kresge Library Exterior Wall | No | 160000 | 160000 | 4850 | 160000
Fund Number 70593
Status: Bidding Engineering
Project Completion Date: August, 2007
Comments: Study indicated increase complexity
Nursing Lab Renovation | No | 155000 | 155000 | 94360 | 155000
Fund Number 70605
Status: Construction - 95%
Projected Completion Date: September, 2005
Comments: Waiting on newly ordered furniture
RAC Flooring Project(Campus Rec Carpet/Pioneer Rm. Impr) | No | 105000 | 155000 | 132832 | 155000
Fund Number 70579
Status: 100% complete - To be closed in next 60 days
Project Completion Date: September 2005
Comments: Waiting on invoice
Varner Garden Plaza | No | 37700 | 157200 | 116818 | 157200
Fund Number 70543
Status: Original scope complete, add'l work added
Project Completion Date: November 2005
Comment: Irrigation was recently added.
ODH Classroom Construction | No | 150000 | 150000 | 139527 | 139527
Fund Number 70584
Status: To be closed in next 30 days - letter sent
Project Completion Date: September 2005
Rosen Writing Center/Kresge Library | No | 150000 | 150000 | 0 | 150000
Fund Number 70611
Status: Final Design Stage
Project Completion Date: May 2006
Solar Electrical Project | No | 135000 | 135000 | 133175 | 135000
Fund Number 70563
Status: To be closed in next 30 days
Project Completion Date: September 2005
MBH Repairs - Roof/Plaster/Windows | No | 130100 | 133350 | 121924.74 | 133350
Fund Number 70580
Status: Construction 99% - completing punch list
Project Completion Date: November 2005
Parking Structure & Police Station | No | 120000 | 120000 | 15062.91 | 120000
Fund Number 70582
Status: On Hold
Project Completion Date: On Hold
Comment: On Hold
MBHEI & SHP (Smart Zone Site Development) | No | 103844 | 103844 | 0 | 103844
Fund Number 70618
Status: Work has begun w/ in-house trades & contractors
Project Completion Date: Dec 2005
Ground Building Sewer | No | 95000 | 95000 | 91436 | 95000
Fund Number 70595
Status: To be closed in next 30 days
Project Completion Date: July 2005
Comment: Just received final permit, paying last payment
ODH 207-209 Classrooms | No | 95000 | 95000 | 81152 | 81152
Fund Number 70598
Status: To be closed in next 30 days - letter sent
Project Completion Date: August 2005
Golf Course Club House | No | 95000 | 95000 | 93345 | 93345
Fund Number 70583
Status: To be closed in next 30 days - letter sent
Project Completion Date: September 2004
Soccer Stadium | No | 70000 | 70000 | 46375 | 70000
Fund Number 70562
Status: Hold
Project Completion Date: Hold
CHP Boiler Instrumentation | No | 60000 | 60000 | 9350 | 60000
Fund Number 70601
Status: Investigation - 25%
Project Completion Date: October, 2005
RAC Racquetball Court No 5 | No | 25000 | 55000 | 44331 | 55000
Fund Number 70602
Status: Construction - 90%
Project Completion Date: September, 2005
Comment: Changing doors and fans per user
Student Apartment Furniture | No | 50000 | 50000 | 0 | 50000
Fund Number 70609
Status: Items ordered
Project Completion Date: November 2005
Golf Course Fuel Tanks | No | 52000 | 52000 | 0 | 52000
Fund Number 70613
Status: Engineering Development
Project Completion Date: May 2006
Comment: Currently estimated budget is $ 94,000
TOTAL PROJECTS IN PROGRESS |  | 3323644 | 4060698 | 2454785.5 | 4030957

## Closed Projected
Projects in Progress - CLOSED | JCOS Approval Req'd Approved | Original Budget | Revised Project Budget | Actual Expenditures to Date | Forecast of Final Cost
NFH Addition/Renovation | No | 2170000 | 2171300 | 1682842 | 1682842
Fund Number 70186
Status: Paperwork sent to Accounting to close
Projected Completion Date: September 2005
Comment: State approval was not necessary because it was for multiple building projects and as separate buildings it did not need state approval
Room 202 ODH Rehab | No | 690000 | 690000 | 680099 | 680099
Fund Number 70574
Status: Closed
Projected Completion Date: Completed
Classroom Conversion | No | 88700 | 894696 | 423842.36 | 423842.36
Fund Number 70165
Status: Paperwork sent to Accounting to close
Project Completion Date: September 2005
Campus Master Plan | No | 400000 | 406700 | 346847 | 346847
Fund Number 70501
Status: Paperwork sent to Accounting to close
Project Completion Date: September 2005
SEHS Building | No | 400000 | 400000 | 431982 | 431982
Fund Number 70524
Status: Paperwork sent to Accounting to close
Project Completion Date: September 2005
Shotwell-MB Health | No | 275000 | 300000 | 299967 | 299967
Fund Number 70537
Status: Closed 2002
Project Completion Date: 2002
East Campus Telecommunications | No | 230000 | 230000 | 229492 | 229492
Fund Number 70596
Status: Closed
Project Completion Date: July 2005
Fast Track Banner Alum | No | 185000 | 200723 | 200000 | 200000
Fund Number 70516
Status: Closed 2002
Project Completion Date: July 2002
Ravine Storm Water | No | 160000 | 160000 | 152547 | 152547
Fund Number 70591
Status: Closed
Project Completion Date: September 2005
Sewer Connection | No | 69000 | 125000 | 115627 | 115627
Fund Number 70570
Status: Closed
Project Completion Date: December 2004
Comment: Original estimate was pre-design
MBH Heating/Hot Water | No | 81500 | 116500 | 115900 | 115900
Fund Number 70575
Status: Closed
Project Completion Date: April 2004
TOTAL PROJECTS IN PROGRESS |  | 4749200 | 5694919 | 4679145.36 | 4679145.36